# Ambassador Scaling Project — Overview

Prepared by: Jessica Bowman     Date: July 6, 2026     To: Matthew     Target Go-Live: July 18, 2026

# What This Project Is

We are building an automated AI agent system to scale the Gracelyn University Ambassador Program to 100,000 ambassadors. The system consists of 11 Catalyst functions (automated agents) that handle every stage of the ambassador lifecycle — recruiting, onboarding, engagement, compliance, support, and payouts — without manual staff intervention.

All 15 design documents are locked. We are now in the 2-week implementation sprint targeting go-live July 18, 2026.

# The 11 Agents

| Agent | Purpose |
| --- | --- |
| Agent 0 | Research & Intelligence — VIP prospect scoring, feeds all others |
| Agent 1A | Recruiting — database email outreach |
| Agent 1B | Recruiting — social media outreach |
| Agent 1C | Recruiting — paid ads (Meta + Google) |
| Agent 1D | Recruiting — lead capture |
| Agent 2 | Onboarding — compliance form, win-back, auto-approval |
| Agent 3 | Engagement — weekly touchpoints, story content, VIP tiers |
| Agent 4 | Compliance Oversight — SLA tracking, auditing, reporting |
| Agent 5 | Ambassador Support — portal chat, escalation |
| Agent 5A | Setup Validation — go/no-go gate before anything goes live |
| Agent 6 | Story Content Intake — feeds Agent 3 |

# Two-Week Timeline

| Week | Dates | Goal | Key Tasks |
| --- | --- | --- | --- |
| Week 1 | Jul 7–11 | Build everything in parallel | Jessica builds all CRM fields, WorkDrive folders, Zoho Forms, and Flows Claude Code writes all 11 agent functions Dr. Flippen opens Wise + Tremendous accounts and confirms policy variables Content gaps drafted (lead magnets, Agent 5 knowledge base) |
| Week 2 | Jul 14–18 | Deploy, test, launch | Make.com scenarios built; all agents deployed to Catalyst Agent 5A validation gate runs — must pass before anything goes live End-to-end testing with a real form submission First ambassador cohort activated July 18 |

# Technology Stack

| Layer | Tool |
| --- | --- |
| Agent runtime | Zoho Catalyst (Node.js) |
| CRM | Zoho CRM v8 |
| Payments | PayPal (launch) + Wise / Tremendous (international, fast-follow) |
| Social posting | Ayrshare |
| Paid ads | Meta Ads + Google Ads |
| Video | HeyGen (Dr. Flippen avatar) |
| AI | Anthropic Claude + OpenAI (Ambassador Support portal) |
| Automation | Make.com + Zoho Flow |
| Ambassador portal | WordPress |

# Execution Lanes

| Lane | Owner | Responsibility |
| --- | --- | --- |
| Infrastructure & UI | Jessica Bowman | CRM fields, forms, flows, WorkDrive folders, deployment to Catalyst |
| Agent code | Claude Code (AI) | All 11 Catalyst functions — written and reviewed against design documents |
| Content & specs | Claude (AI) | Lead magnets, knowledge base, Make.com scenario specs, WordPress change specs |
| Sign-off & accounts | Dr. Flippen | Policy variables, Wise/Tremendous accounts, content approval |

# Current Status

✓ Design complete — All 15 build documents locked. No open design decisions.
✓ Project tasks loaded — All 39 tasks with due dates and owners are live in Zoho Projects.
✓ Build sprint begins — July 7, 2026.
Critical path: Wise/Tremendous verification → CRM fields → Agent 5A pass → deploy → test → launch

# Key Risk

Wise and Tremendous account verification has a 1–3 business day external clock and must be opened first thing Monday, July 7. If verification does not clear by July 10, we launch on PayPal only and add international routing as a fast-follow within days. All other risks are within our control.

All tasks, due dates, and owners are tracked in Zoho Projects. Questions: jessica.bowman@gracelyn.edu